## Read Me
TRUE | START
FALSE | END
FALSE

## W90 MP
N | Description - MP Piling (non drilling) | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit to sheltered area or Yard | Given by distance | 7.1 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
2 | Arrival and mooring | 1 | 2.5 | 18 | 50% | 0.5 | 1.5 | FALSE | START | FALSE
3 | Loading each Monopile | 8 | 2.5 | 18 | 50% | 4 | 12 | FALSE | FALSE | FALSE
4 | Sea-fastening and departure | 3 | 2.5 | 18 | 50% | 1.5 | 4.5 | FALSE | END | FALSE
5 | Transit to Wind Farm | Given by distance | 7.1 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
6 | Arrival Wind Farm, positioning and preperations | 2 | 6 | 18 | 50% | 1 | 3 | FALSE | FALSE | START
7 | Move MP from setback to Main Hook position | 2 | 6 | 18 | 50% | 1 | 3 | FALSE | FALSE | FALSE
8 | Monopile is lowered to the seabed and positioned accurately. | 4 | 2.5 | 18 | 50% | 2 | 6 | FALSE | FALSE | FALSE
9 | Monopile is driven into the seabed using a vibro-hammer (initial) and then a hydraulic impact hammer (main driving). (Ad 10 horus if drilling) | 10 | 2.5 | 18 | 50% | 5 | 15 | FALSE | FALSE | FALSE
10 | Check and Verifications | 2 | 2.5 | 18 | 50% | 1 | 3 | FALSE | FALSE | FALSE
11 | Move to next location | 1 | 6 | 18 | 50% | 0.5 | 1.5 | FALSE | FALSE | END

## JUV MP
N | Description | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit to sheltered area or Yard | Given by distance | 4 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
2 | Arrival and mooring | 1 | 1 | 18 | 50% | 0.5 | 1.5 | FALSE | START | FALSE
3 | Loading each Monopile | 8 | 1.5 | 11 | 50% | 4 | 12 | FALSE | FALSE | FALSE
4 | Sea-fastening and departure | 3 | 1 | 11 | 50% | 1.5 | 4.5 | FALSE | END | FALSE
5 | Transit to Wind Farm | Given by distance | 4 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
6 | Arrival Wind Farm, positioning and preperations | 2 | 2.5 | 14 | 50% | 1 | 3 | FALSE | FALSE | END
7 | Move MP from DECK to Main Hook position | 6 | 1.5 | 11 | 50% | 3 | 9 | FALSE | FALSE | FALSE
8 | Monopile is lowered to the seabed and positioned accurately. | 4 | 1.5 | 11 | 50% | 2 | 6 | FALSE | FALSE | FALSE
9 | Monopile is driven into the seabed using a vibro-hammer (initial) and then a hydraulic impact hammer (main driving). (Ad 10 horus if drilling) | 10 | 2 | 11 | 50% | 5 | 15 | FALSE | FALSE | FALSE
10 | Check and Verifications | 2 | 2 | 11 | 50% | 1 | 3 | FALSE | FALSE | FALSE
11 | Move to next location | 1 | 4 | 14 | 50% | 0.5 | 1.5 | FALSE | FALSE | END

## FIV MP
N | Description - MP Piling (non drilling) | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit to sheltered area or Yard | Given by distance | 4 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
2 | Arrival and mooring | 1 | 1 | 18 | 50% | 0.5 | 1.5 | FALSE | START | FALSE
3 | Loading each Monopile | 8 | 1.5 | 11 | 50% | 4 | 12 | FALSE | FALSE | FALSE
4 | Sea-fastening and departure | 3 | 1 | 11 | 50% | 1.5 | 4.5 | FALSE | END | FALSE
5 | Transit to Wind Farm | Given by distance | 4 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
6 | Arrival Wind Farm, positioning and preperations | 2 | 2.5 | 14 | 50% | 1 | 3 | FALSE | FALSE | END
7 | Move MP from DECK to Main Hook position | 6 | 1.5 | 11 | 50% | 3 | 9 | FALSE | FALSE | FALSE
8 | Monopile is lowered to the seabed and positioned accurately. | 4 | 1.5 | 11 | 50% | 2 | 6 | FALSE | FALSE | FALSE
9 | Monopile is driven into the seabed using a vibro-hammer (initial) and then a hydraulic impact hammer (main driving). (Ad 10 horus if drilling) | 10 | 2 | 11 | 50% | 5 | 15 | FALSE | FALSE | FALSE
10 | Check and Verifications | 2 | 2 | 11 | 50% | 1 | 3 | FALSE | FALSE | FALSE
11 | Move to next location | 1 | 4 | 14 | 50% | 0.5 | 1.5 | FALSE | FALSE | END

## W90 WTG
N | Description | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation | Parallell 1 | Parallell 2
1 | Transit @10kts. Prepare for loading | 5 | 7.1 | 18 | 2.5 | 50% | 7.5 | TRUE | FALSE | FALSE | FALSE | FALSE
2 | Position W90 for loading from barges (W90 in DP mode) | 2 | 2.5 | 18 | 1 | 50% | 3 | FALSE | START | FALSE | FALSE | FALSE
3 | 8 Transport barges loaded with 8 TT main towers (32 sections total) | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | TRUE | FALSE
4 | Move TT barge 1 alongside W90 starboard (2 tugs). Moore to W90 | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | TRUE | FALSE
5 | Connect W90 SDC and lift TT main section 1 to W90 catwalk | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | TRUE | FALSE
6 | Lift main section 1 into vertical by STH, then into main tower to AP1. | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | TRUE | FALSE
7 | Connect W90 SDC and lift TT main section2 to W90 catwalk | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | TRUE | FALSE
8 | Lift main section 2 into vertical by STH, then into main tower to AP1. | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | TRUE | FALSE
9 | Bolt TT section 1 and 2 together in AP1 | 3 | 2.5 | 18 | 1.5 | 50% | 4.5 | FALSE | FALSE | FALSE | TRUE | FALSE
10 | Connect W90 SDC and lift TT main section 3 to W90 catwalk | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | TRUE | FALSE
11 | Lift main section 3 into vertical by STH, then into main tower to AP1. | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | TRUE | FALSE
12 | Bolt TT section 2 and 3 together in AP1 | 3 | 2.5 | 18 | 1.5 | 50% | 4.5 | FALSE | FALSE | FALSE | TRUE | FALSE
13 | Connect W90 SDC and lift TT main section 4 to W90 catwalk | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | TRUE | FALSE
14 | Lift main section 4 into vertical by STH, then into main tower to AP1. | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | TRUE | FALSE
15 | Bolt TT section 3 and 4 together in AP1 and seafasten in setback | 3 | 2.5 | 18 | 1.5 | 50% | 4.5 | FALSE | FALSE | FALSE | TRUE | FALSE
16 | 1 Transport barge loaded with 8 vertical TT Lower sections ready in sheltered area | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | FALSE | TRUE
17 | Move TT barge alongside W90 port side (2 tugs). Moore to W90. | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | FALSE | TRUE
18 | PDC lift 8 lower TT sections onto W90 to skid landing area port side. | 10 | 2.5 | 18 | 5 | 50% | 15 | FALSE | FALSE | FALSE | FALSE | TRUE
19 | Skid and seafasten all lower TT tubes in W90 deck storage area | 9 | 2.5 | 18 | 4.5 | 50% | 13.5 | FALSE | FALSE | FALSE | FALSE | TRUE
20 | 2 transport barges loaded with 8 nacelles (30x10x10m, ea1400t) ready | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | FALSE | TRUE
21 | Move Nacelle barge alongside W90 port side (2 tugs). Moore to W90. | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | FALSE | TRUE
22 | PDC lift 8 Nacelles onto W90 to skid landing area port side. | 28 | 2.5 | 18 | 14 | 50% | 42 | FALSE | FALSE | FALSE | FALSE | TRUE
23 | Skid and seafasten all Nacelles in W90 deck storage area | 26 | 2.5 | 18 | 13 | 50% | 39 | FALSE | FALSE | FALSE | FALSE | TRUE
24 | 4 Transport barges with 24 rotor blades (for 8WTG's) Ready in sheltered area | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | FALSE | FALSE
25 | Move Rotor Blade barge alongside W90 port side (2 tugs). Moore to W90. | 1 | 2.5 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | FALSE | FALSE
26 | Offload from barges and store 24 rotor blades onboard W90 blade rack. | 44 | 2.5 | 18 | 22 | 50% | 66 | FALSE | FALSE | FALSE | FALSE | FALSE
27 | Prepare for transit, manouver W90 to open sea. | 2 | 2.5 | 18 | 1 | 50% | 3 | FALSE | END | FALSE | FALSE | FALSE
28 | Transit @10kts. back to windfarm area | 5 | 2.5 | 18 | 5 | 100% | 10 | TRUE | FALSE | FALSE | FALSE | FALSE
29 | Ballast W90 to operating draft approaching windpark location | 5 | 2.5 | 18 | 5 | 100% | 10 | FALSE | FALSE | START | FALSE | FALSE
30 | Position W90 over foundation, fully loaded, 8 WTG sets | 1 | 6 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | FALSE | FALSE
31 | Move lower TT from port store position to MAP | 1 | 6 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | FALSE | FALSE
32 | Move main TT from stb store position to SAP | 1 | 6 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | FALSE | FALSE
33 | Lift main TT up and transverse over top of lower TT | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
34 | Position and bolt up lower and main TT in MAP | 2 | 6 | 18 | 1 | 50% | 3 | FALSE | FALSE | FALSE | FALSE | FALSE
35 | Move TT gripping tool to SAP | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
36 | Main hoist connect nacelle yoke | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
37 | Main hoist install elevator to TT | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
38 | Main hoist lift nacelle up, release transport skid | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
39 | Main hoist lift nacelle up and over top of TT | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
40 | Position and bolt nacelle to top of TT | 2 | 6 | 18 | 1 | 50% | 3 | FALSE | FALSE | FALSE | FALSE | FALSE
41 | Prepare fwd horizontal guides for TT move | 1 | 6 | 18 | 0.5 | 50% | 1.5 | FALSE | FALSE | FALSE | FALSE | FALSE
42 | Prepare main hoist yoke, diconnect nacelle, lift on TT | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
43 | Lift TT with nacelle, move forward to blade inst. position | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
44 | Move blade 1 from aft center storage to blade trolley | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
45 | Move blade and trolley to fwd position | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
46 | Blade installer pick up blade and move to nacelle hub | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
47 | Install blade 1 to hub, bolt up | 1.5 | 6 | 18 | 0.75 | 50% | 2.25 | FALSE | FALSE | FALSE | FALSE | FALSE
48 | Rotate hub 120 deg | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
49 | Move blade 2 from aft center storage to blade trolley | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
50 | Move blade and trolley to fwd position | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
51 | Blade installer pick up blade and move to nacelle hub | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
52 | Install blade 2 to hub, bolt up | 1.5 | 6 | 18 | 0.75 | 50% | 2.25 | FALSE | FALSE | FALSE | FALSE | FALSE
53 | Rotate hub 120 deg | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
54 | Move blade 3 from aft center storage to blade trolley | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
55 | Move blade and trolley to fwd position | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
56 | Blade installer pick up blade and move to nacelle hub | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
57 | Install blade 3 to hub, bolt up | 1.5 | 6 | 18 | 0.75 | 50% | 2.25 | FALSE | FALSE | FALSE | FALSE | FALSE
58 | Align W90 and WTG for connection to TP-BF foundation. | 0.5 | 4 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
59 | Lower WTG onto TP- foundation, bolt up | 2 | 4 | 18 | 1 | 50% | 3 | FALSE | FALSE | FALSE | FALSE | FALSE
60 | Prepare to disconnect from WTG | 0.5 | 4 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | FALSE | FALSE | FALSE
61 | Move W90 0.5NM to next location | 0.5 | 6 | 18 | 0.25 | 50% | 0.75 | FALSE | FALSE | END | FALSE | FALSE

## JUV WTG
N | Description | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit into port | Transit | NA | NA |  |  |  | TRUE | FALSE | FALSE
2 | port entry to load-out quay | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
3 | jack-up at port / quay | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
4 | preparatory works (e.g. gangway secured, backloading Owner, etc.) | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
5 | handover main crane from Owner to WTG OEM | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
6 | backloading WTG items incl. TP-cover | 2 | NA | 14 | 60% | 3 | 5 | FALSE | FALSE | FALSE
7 | Loading of WTG tower | 2.5 | NA | 10.5 | 60% | 3.75 | 6.25 | FALSE | START | FALSE
8 | Loading of WTG nacelle | 2.5 | NA | 10.5 | 60% | 3.75 | 6.25 | FALSE | FALSE | FALSE
9 | Loading of blades for ( Time per blade x Number of turbines carried) | 1.75 | NA | 8.25 | 58.82% | 2.5 | 4.25 | FALSE | FALSE | FALSE
10 | Loading of auxiliary equipment of WTG-OEM | 2 | NA | 12 | 55.56% | 2.5 | 4.5 | FALSE | END | FALSE
11 | handover main crane from WTG OEM to Owner | 1 | NA | NA | 60% | 1.5 | 2.5 | FALSE | FALSE | FALSE
12 | Finish load-out operations and prepare for sailing jack-down at port | 1 | NA | NA | 60% | 1.5 | 2.5 | FALSE | FALSE | FALSE
13 | port exit | 0.5 | NA | NA | 50% | 0.5 | 1 | FALSE | FALSE | FALSE
14 | Transit to Project location | Transit | NA | NA |  |  |  | TRUE | FALSE | FALSE
15 | DP trials before entering Dreekant OWF borders | 1 | 3 | NA | 50% | 1 | 2 | FALSE | FALSE | FALSE
16 | pre-loading and jack-up to working height | 2 | 2 | 13.5 | 66.67% | 4 | 6 | FALSE | FALSE | FALSE
17 | handover main crane from Owner to WTG OEM | 1 | 2 | 13.5 | 66.67% | 2 | 3 | FALSE | FALSE | FALSE
18 | preparation of TP and TP-cover removal | 2 | NA | 12 | 42.86% | 1.5 | 3.5 | FALSE | FALSE | FALSE
19 | prepare for tower lifting | 3 | NA | 12 | 40% | 2 | 5 | FALSE | FALSE | START
20 | installation of tower (safe to safe) | 1 | NA | 10.5 | 83.33% | 5 | 6 | FALSE | FALSE | FALSE
21 | de-rigging tower | 1 | NA | 12 | 50% | 1 | 2 | FALSE | FALSE | FALSE
22 | prepare for nacelle lifting | 1 | NA | 12 | 50% | 1 | 2 | FALSE | FALSE | FALSE
23 | installation of nacelle (safe to safe) | 2.5 | NA | 10.5 | 61.54% | 4 | 6.5 | FALSE | FALSE | FALSE
24 | de-rigging nacelle | 1 | NA | 12 | 50% | 1 | 2 | FALSE | FALSE | FALSE
25 | prepare for blade lifting | 1 | NA | 10.5 | 50% | 1 | 2 | FALSE | FALSE | FALSE
26 | installation of blade 1 (per blade & safe to safe) | 2.5 | NA | 8.25 | 60% | 3.75 | 6.25 | FALSE | FALSE | FALSE
27 | installation of blade 2 (per blade & safe to safe) | 2.5 | NA | 8.25 | 60% | 3.75 | 6.25 | FALSE | FALSE | FALSE
28 | installation of blade 3 (per blade & safe to safe) | 2.5 | NA | 8.25 | 60% | 3.75 | 6.25 | FALSE | FALSE | FALSE
29 | de-rigging blades | 3 | NA | 10.5 | 50% | 3 | 6 | FALSE | FALSE | FALSE
30 | WTG completion works | 1 | NA | 13.5 | 66.67% | 2 | 3 | FALSE | FALSE | FALSE
31 | handover main crane from WTG OEM to Owner | 1 | NA | 13.5 | 66.67% | 2 | 3 | FALSE | FALSE | FALSE
32 | preparation works before jack-down | 1 | NA | 13.5 | 66.67% | 2 | 3 | FALSE | FALSE | FALSE
33 | jack-down at location | 0.5 | NA | 13.5 | 50% | 0.5 | 1 | FALSE | FALSE | FALSE
34 | Relocate to next asset | 0.5 | 3 | NA | 50% | 0.5 | 1 | FALSE | FALSE | END

## FIV WTG
N | Description | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit into port | Transit | NA | NA |  |  |  | TRUE | FALSE | FALSE
2 | port entry to load-out quay | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
3 | jmooring port / quay | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
4 | preparatory works (e.g. gangway secured, backloading Owner, etc.) | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
5 | handover main crane from Owner to WTG OEM | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
6 | backloading WTG items incl. TP-cover | 2 | NA | 14 | 60% | 3 | 5 | FALSE | FALSE | FALSE
7 | Loading of WTG tower | 2.5 | NA | 10.5 | 60% | 3.75 | 6.25 | FALSE | START | FALSE
8 | Loading of WTG nacelle | 2.5 | NA | 10.5 | 60% | 3.75 | 6.25 | FALSE | FALSE | FALSE
9 | Loading of blades for ( Time per blade x Number of turbines carried) | 1.75 | NA | 8.25 | 58.82% | 2.5 | 4.25 | FALSE | FALSE | FALSE
10 | Loading of auxiliary equipment of WTG-OEM | 2 | NA | 12 | 55.56% | 2.5 | 4.5 | FALSE | END | FALSE
11 | handover main crane from WTG OEM to Owner | 1 | NA | NA | 60% | 1.5 | 2.5 | FALSE | FALSE | FALSE
12 | Finish load-out operations and prepare for sailing jack-down at port | 1 | NA | NA | 60% | 1.5 | 2.5 | FALSE | FALSE | FALSE
13 | port exit | 0.5 | NA | NA | 50% | 0.5 | 1 | FALSE | FALSE | FALSE
14 | Transit to Project location | Transit | NA | NA |  |  |  | TRUE | FALSE | FALSE
15 | DP positioning on foundation | 1 | 2.5 | 15 | 50% | 1 | 2 | FALSE | FALSE | START
16 | TP / interface inspection | 1 | 2 | 15 | 80% | 4 | 5 | FALSE | FALSE | FALSE
17 | Lift tower section 1 | 1 | 2 | 14 | 66.67% | 2 | 3 | FALSE | FALSE | FALSE
18 | Set‑down & bolt tower section 1 | 1.5 | 1.5 | 12 | 50% | 1.5 | 3 | FALSE | FALSE | FALSE
19 | Lift/set tower section 2 | 3 | 1.5 | 12 | 40% | 2 | 5 | FALSE | FALSE | FALSE
20 | Lift/set tower section 3 (if any) | 3 | 1.5 | 12 | 62.5% | 5 | 8 | FALSE | FALSE | FALSE
21 | Lift nacelle from deck | 1.5 | 1.5 | 11 | 40% | 1 | 2.5 | FALSE | FALSE | FALSE
22 | Nacelle overboard & set‑down | 2 | 1.25 | 10 | 33.33% | 1 | 3 | FALSE | FALSE | FALSE
23 | Lift blade 1 | 1 | 1.5 | 11 | 80% | 4 | 5 | FALSE | FALSE | FALSE
24 | Blade 1 hub mating & bolting | 2 | 1.5 | 10 | 33.33% | 1 | 3 | FALSE | FALSE | FALSE
25 | Blade 2 install | 4 | 1.25 | 10 | 20% | 1 | 5 | FALSE | FALSE | FALSE
26 | Blade 3 install | 4 | 1.25 | 10 | 48.39% | 3.75 | 7.75 | FALSE | FALSE | FALSE
27 | Final bolting & torqueing | 2 | 2 | 15 | 65.22% | 3.75 | 5.75 | FALSE | FALSE | FALSE
28 | Mechanical completion checks | 2 | 2.5 | 18 | 65.22% | 3.75 | 5.75 | FALSE | FALSE | FALSE
29 | Clear turbine & move‑off to next location | 3 | 3 | 18 | 50% | 3 | 6 | FALSE | FALSE | END